## InputParameters
Total Test Cases |  |  | Number of Automation Engineers |  | 2
Test Suite A |  | 100 | Capacity Per Day (Hrs) |  | 16
Test Suite B |  | 150 | Contingency |  | 20%
Test Suite C |  | 200
Total |  | 450
Test Cases - Complexity (Definition) |  |  | Automation TC Development time against Complexity (In Hours)
Complexity | Percentage | TCs | Complexity | Development Time | Total
Simple | 60% | 270 | Simple | 2 | 540
Medium | 30% | 135 | Medium | 4 | 540
Complex | 10% | 45 | Complex | 8 | 360
|  |  | Total Development time (Automated TCs) |  | 1440
Manual execution time against complexity |  |  | Total Development time (Hrs) |  | 1728
Complexity | Development Time(mins) | Total | Total Script development time - In Days (1 Engineer) |  | 216
Simple | 30 | 8100 | Total Script development time - In Days (All Engineer) |  | 108
Medium | 60 | 8100
Complex | 120 | 5400
Total execution time (In Mins) |  | 21600
Total execution time (In Hours) |  | 360 | Expected Throughput Per Day(Considering all engineers) |  | 4.1667
Manual Efforts for TC execution |  | 45 | Expected Throughput Per Sprint (Considering 2 weeks Sprint + All Engineers) |  | 41.6667
|  |  | Total Sprints Expected |  | 10.8
Average Efforts per test case - Manual (Hrs) |  | 0.8 | Total ROI Per TC |  | 0.8
Note on F4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: - Framework Development - Environment specific changes - CI/CD << add parameters specific to your project >>

## TC Development Plan + ROI
Autoamtion Test Case delivery plan
Sprint | Manual TCs | Automated TCs | ROI (Hrs/Exec) | Cumulative ROI (Hrs/Exec) | ROI (PDs/Exec¦Cumulative) | Manual Efforts(Hrs)
S1 | 450 | 0 | 0 | 0 | 0 | 360
S2 | 408.3333 | 41.6667 | 33.3333 | 33.3333 | 4.1667 | 326.6667
S3 | 366.6667 | 83.3333 | 66.6667 | 100 | 12.5 | 293.3333
S4 | 325 | 125 | 100 | 200 | 25 | 260
S5 | 283.3333 | 166.6667 | 133.3333 | 333.3333 | 41.6667 | 226.6667
S6 | 241.6667 | 208.3333 | 166.6667 | 500 | 62.5 | 193.3333
S7 | 200 | 250 | 200 | 700 | 87.5 | 160
S8 | 158.3333 | 291.6667 | 233.3333 | 933.3333 | 116.6667 | 126.6667
S9 | 116.6667 | 333.3333 | 266.6667 | 1200 | 150 | 93.3333
S10 | 75 | 375 | 300 | 1500 | 187.5 | 60
S11 | 33.3333 | 416.6667 | 333.3333 | 1833.3333 | 229.1667 | 26.6667
S12 | 0 | 450 | 360 | 2193.3333 | 274.1667 | 0

## SprintProposal
Sprint Week 0 |  | Sprint Week 1 |  | Sprint Week 2
|  | Day 1 | Back log item briefing and assignment in Planning Call - 0.5 hr | Day 6 | Daily updates in scrum call
|  |  | Identifying dependencies and highlighting them |  | Dependency Management
|  |  | Scripting, Execution, maintenance activity |  | Scripting, Execution, maintenance activity
|  | Day 2 | Daily updates in scrum call | Day 7 | Daily updates in scrum call
|  |  | Dependency Management |  | Dependency Management
|  |  | Scripting, Execution, maintenance activity |  | Scripting, Execution, maintenance activity
Sprint Retrospective Meeting For -1 Sprint - 1 hr
Understand the issue and implement mitigation
|  | Day 3 | Daily updates in scrum call | Day 8 | Daily updates in scrum call
|  |  | Dependency Management |  | Dependency Management
|  |  | Scripting, Execution, maintenance activity |  | Scripting, Execution, maintenance activity
Day -2 | Backlog Grooming - Test Case identification (1Hr) | Day 4 | Daily updates in scrum call | Day 9 | Daily updates in scrum call
| Identifying dependencies and highlighting them |  | Dependency Management |  | Dependency Management
| Scripting, Execution, maintenance activity - From -1 sprint |  | Scripting, Execution, maintenance activity |  | Review comment incorporation, Execution, maintenance activity
| Collate back log items for next 2 weeks and create user stories, tasks in JIRA should factor |  |  |  | Collate back log items for next 2 weeks and create user stories, tasks in JIRA should factor
| * New scripting/migration activity identification for next sprint |  |  |  | * New scripting/migration activity identification for next sprint
| * Execution/maintenance |  | * Defects identified by automation |  | * Execution/maintenance
| * Planned functional activity where automation can be leveraged |  | * Quantification of effort savings achieved by automation |  | * Planned functional activity where automation can be leveraged
Day -1 | Backlog Grooming - Test Case identification Cont... (1Hr) | Day 5 | Daily updates in scrum call | Day 10 | Bi-Weekly status update/ Sprint End Demos to stake holders.
| Dependency Management |  | Dependency Management |  | Deliver scripts to Functional team for review
| Scripting, Execution, maintenance activity - From -1 sprint |  | Scripting, Execution, maintenance activity |  | Review comment incorporation, Execution, maintenance activity
Sprint Planning meeting - .5 hr
* Update capacity of automation team member
* Prioritize backlog for next sprint